CodeSprint 3.0

45 Days of DSA Practice

Organized by USC KIIT

## Event Overview

CodeSprint 3.0 is a 45-day coding challenge organized by USC KIIT, designed to help students build strong problem-solving skills through daily DSA practice. Participants will receive 2 coding questions every day through the official CodeSprint website platform.

The challenge focuses on improving consistency, logical thinking, coding speed, and interview preparation through a structured and competitive learning environment.

## Event Format

| Duration | 45 Days |
| --- | --- |
| Questions/Day | 2 Questions |
| Platform | Official CodeSprint Website |
| Difficulty | Beginner to Advanced |
| Participation | Daily Required |

## Objectives

- Encourage daily coding practice and discipline

- Improve problem-solving and analytical thinking

- Strengthen DSA concepts for placements & internships

- Increase coding confidence among participants

- Provide a structured roadmap for interview preparation

## DSA Topics Covered

- Arrays & Strings

- Linked Lists

- Stacks & Queues

- Trees & BST

- Recursion & Backtracking

- Dynamic Programming

- Graph Algorithms

- Sorting & Searching

## Execution Timeline

| Date / Phase | Activity |
| --- | --- |
| 30 April | Web Dev team meeting — website, dashboard, leaderboard, platform testing |
| 5 May | Announcement poster release & social media promo |
| 10 May | Official announcement email + Website goes live + Registration opens |
| 11 May | Promotional mail — Round 1 |
| 13 May | Promotional mail — Round 2 + Challenge kickoff reminder |
| 15 May | Closing Soon post (social media) & Closing Soon email to students |

## Question Preparation

All 90 coding questions (2/day x 45 days) will be prepared and verified before the challenge begins. The preparation process includes:

- Topic-wise division and difficulty balancing

- Test case validation and solution verification

- Platform compatibility checking

## Participant Rewards

Students who successfully complete all daily challenges will receive:

- Certificate of Completion

- Winner & Top Performer Perks

- Community Recognition

- Special Opportunities & Benefits

## Promotion Plan

- Instagram Announcement Posts

- WhatsApp Community Promotions

- Email Campaigns (5 May, 7 May, 10 May, 13 May)

## Expected Outcomes

Through CodeSprint 3.0, participants will develop strong coding habits, improve technical interview preparation, gain confidence in DSA problem-solving, build consistency in competitive coding, and become part of an active coding community.

USC KIIT